- UNIVERSITY OF GHANA

- DEPARTMENT OF COMPUTER ENGINEERING

- SCHOOL OF ENGINEERING SCIENCES

- COLLEGE OF BASIC AND APPLIED SCIENCES

- SECOND SEMESTER – 2025/2026 ACADEMIC YEAR

- CPEN 438 - Advanced Computer Organization and Architecture

- Course Instructor: Prof. Robert A. Sowah

Project 2:

GhanaCore-5 - Five-Stage Pipelined Processor for MoMo Transaction Codes

Group 7

- WEEKLY COURSE PROJECT REPORT

Course Code and Title: CPEN 438 - Computer Architecture
Project Title: Project 2: GhanaCore-5, Five-Stage Pipelined Processor for MoMo Transaction Codes
Team Number/Name: Group 7
Reporting Week: Week 1  			Period: [03/08/26] to [07/08/26]
Team Leader/Reporter: Ahmed Fareed Opare     Submission Date: 19/08/2026

- 1. Weekly Objective and Progress Summary

Main objective for the week:

Deliver the Week 1 artifacts for GhanaCore-5: a draft MoMo instruction subset with fixed-width encoding; an opcode/format table mapping every field to the IF/ID, ID/EX, EX/MEM, and MEM/WB pipeline registers; and a review of Patterson & Ditzel (1980) and Patterson & Séquin (1981) that ties their RISC arguments directly to our five-stage, fixed-width design.

Overall project completion: 10%

Summary of progress achieved:

Planned: Draft ISA, opcode/format table, and review of the two required papers, per the project brief.

Completed:

- A 20-instruction MoMo ISA (arithmetic, immediate, branch, load/store, NOP) with full 32-bit R/I/J-type encoding, implemented and unit-checked in isa/isa.py

- A hand-verified MoMo debit routine (balance load → amount+fee arithmetic → SLT+BNE bounds check → balance store), cross-checked against the assembler's output

- The complete opcode/format table, including pipeline-register-field mapping

- Full slide content for both required papers, closing with a slide connecting their RISC arguments directly to our design decisions

Key outcome: The ISA encoding isn't just a paper spec; it's executable and self-verifying. isa/isa.py prints hex/binary for every instruction, giving Week 2's assembler and simulator work a verified foundation to build on.

- 2. Meetings Held

| Date and time | Duration/Mode | Members Present | Main Agenda | Decisions and Outcomes |
| --- | --- | --- | --- | --- |
| 03/08/2026, 7:00 PM | 60 min · Online | Fareed Opare Ahmed, Kwesi Asante Agyepong, Isaac Nii Nortey Barnor, Mohammed Salihu Hamisu | Kickoff: assign Week 1 tasks (ISA/encoding, repository structure, opcode/format table, RISC paper review) and confirm project scope | Tasks assigned per Section 3; five-stage IF/ID/EX/MEM/WB design confirmed; draft ISA due before the Week 1 review meeting |
| 07/08/2026, 4:00 PM | 30 min. Online | Fareed Opare Ahmed, Kwesi Asante Agyepong, Isaac Nii Nortey Barnor, Mohammed Salihu Hamisu | Review Week 1 deliverables: draft MoMo ISA, opcode/format table, RISC paper review | Instruction set finalised at 20 mnemonics (R/I/J, 32-bit fixed width); opcode/pipeline table approved for submission; paper review to be trimmed to one slide per paper |

- 3. Work Completed and Individual Contributions

| Member | Assigned Task | Work Completed | Evidence/Output | Status |
| --- | --- | --- | --- | --- |
| Mohammed Salihu Hamisu | Draft MoMo instruction subset + fixed-width encoding | Defined a 20-instruction ISA (arithmetic, immediate, branch, load/store, NOP) with R/I/J formats; implemented the encoder and assembled the MoMo debit routine. | isa/isa.py; docs/momo_routine.md | Completed |
| Kwesi Asante Agyepong | Repository structure | Set up /isa, /assembler, /simulator, /logisim, /docs layout with README stubs; git-initialised the repo. | README.md; repo folder structure | Completed |
| Ahmed Fareed Opare | Opcode/format table | Documented the R/I/J bit-field layout and the exact IF/ID, ID/EX, EX/MEM, MEM/WB pipeline register contents, cross-checked against isa.py. | docs/opcode_format_table.md; docs/opcode_table.csv | Completed |
| Isaac Nii Nortey Barnor | Paper review (Patterson & Ditzel 1980; Patterson & Séquin 1981) | Wrote full slide content for both papers plus a slide connecting their RISC arguments to the GhanaCore-5 fixed-width, five-stage design. | docs/paper_review_slides.md | Completed |

- 4. Work Process and Technical Activities

Methods, tools, and procedures used:

Designed the instruction formats (R/I/J, 32-bit fixed width, 16 registers) and implemented them in Python (isa/isa.py), which serves as a working encoder/disassembler as well as documentation, rather than a static spec. Referenced RISC I (Patterson & Séquin, 1981) as design precedent for register-window and single-cycle architecture when settling on register count and format widths. Organized the repository into /isa, /assembler, /simulator, /logisim, and /docs, and initialized it under git for version control.

Testing, verification, or review conducted:

Ran isa/isa.py to assemble the MoMo debit routine and hand-verified two encodings against the spec: the BNE bounds-check branch (a 5-word offset, PC-relative to the INSUFFICIENT label) and the J instruction's absolute word address (13, i.e. byte address 52 ÷ 4) to the DONE label. Both matched manual calculations, confirming that the encoder and label-resolution logic are correct. Cross-checked the opcode/format table's pipeline-register field list against isa.py's OPCODE/FUNCT/USES_* tables to keep the two documents synchronized.

- 5. Challenges, Changes, and Corrective Actions

| Challenge or Deviation | Effect on Project | Action Taken/Proposed | Responsible Member |
| --- | --- | --- | --- |
| Team roster and a Week 1 meeting log are not yet captured in this report. | Individual-contribution attribution and the accountability declaration are incomplete pending team input. | Team to confirm member names, meeting date/time/mode, and sign off before submission. | Ahmed Fareed Opare |
| No prior group decision on register count / field widths (e.g. 16 vs. 32 registers) before this week. | Affects opcode bit-field allocation once the assembler and simulator are built on top of it. | Adopted 16 registers (4-bit fields) with 18-bit immediates for Week 1, following RISC I precedent (Patterson & Séquin, 1981); open to revisiting once Week 2 workload profiling starts. | Whole team |

- 6. Plan for the Next Week

| Planned Task or Deliverable | Responsible Member(s) | Deadline | Expected Evidence |
| --- | --- | --- | --- |
| Build MoMo assembler (. s → machine code) extending isa.py's encoder | Whole team | Week 2 report deadline (Wed 2026-08-19, per course schedule) | assembler/ CLI + sample assembled programs |
| Begin cycle-accurate 5-stage pipeline simulator (hazard detection, forwarding, branch resolution) | Whole team | Week 2 report deadline (Wed 2026-08-19, per course schedule) | simulator/ source + a test run against docs/momo_routine.md |
| Start Logisim/Digital datapath + control unit circuit | Whole team | Week 3 report deadline (Sun 2026-08-23) | logisim/ .circ file(s) for the datapath skeleton |

.

- 7. Team Accountability Declaration

We confirm that this report accurately represents the meetings, work completed, individual contributions, challenges, and evidence produced during the reporting week.

Team Leader: Ahmed Fareed Opare 				Date: 19/08/2026

Team Members’ Initials: AFO, KAA, INNB, MSH

Evidence repository/link: https://github.com/Asante8/GhanaCore-5-Group7.git